## Inprogress
Date | Shift | Shift Lead | Requestor/Client Name | Project Number | WO Number | Status | Job Name | Job Type | Region | Receipt Time | Initiation Time | Deadline IST | Delivered Time | Complexity | Total Pages | Operator | QC
2026-09-01 | Shift-1 | Ram Kesavan | Client Name 103 | 2000000 | 5000000000 | QC | Brochure Project Sep 1 | Print | Newyork | 2026-09-01 01:22 | 2026-09-01 01:32 | 2026-09-02 01:32 |  |  |  | Bala
2026-09-01 | Shift-1 | Ram Kesavan | Client Name 104 | 2000001 | 5000000001 | QC | Brochure Project Sep 2 | Posting | Mumbai | 2026-09-01 01:23 | 2026-09-01 01:33 | 2026-09-02 01:33
2026-09-01 | Shift-1 | Ram Kesavan | Client Name 105 | 2000002 | 5000000002 | Inprogress | Brochure Project Sep 3 | Web | London | 2026-09-01 01:24 | 2026-09-01 01:34 | 2026-09-02 01:34 |  |  |  |  | Arjun
2026-09-01 | Shift-1 | Ram Kesavan | Client Name 106 | 2000003 | 5000000003 | Inprogress | Brochure Project Sep 4 | Posting | Newyork | 2026-09-01 01:25 | 2026-09-01 01:35 | 2026-09-02 01:35
2026-09-01 | Shift-1 | Ram Kesavan | Client Name 107 | 2000004 | 5000000004 | Inprogress | Banner Project Sep 1 | Print | Newyork | 2026-09-01 01:26 | 2026-10-11 11:26 | 2026-09-02 01:26 |  |  |  | Bala
2026-09-01 | Shift-1 | Ram Kesavan | Client Name 108 | 2000005 | 5000000005 | QC | Banner Project Sep 2 | Headshot | Newyork | 2026-09-01 01:27 | 2026-09-01 01:46 | 2026-09-02 01:46
2026-10-04 | Shift-1 | Ram Kesavan | Client Name 109 | 2000006 | 5000000006 | Inprogress | Banner Project Sep 3 | Print | Newyork
2026-10-04 | Shift-1 | Ram Kesavan | Client Name 110 | 2000007 | 5000000007 | TBI | Flyer Project Sep 1 | Headshot | Newyork | 2026-10-04 22:33 | 2026-10-06 06:46 | 2026-10-05 22:33 |  |  |  | Operator 2
2026-10-05 | Shift-1 | Ram Kesavan | Client Name 111 | 2000008 | 5000000008 | TBI | Flyer Project Sep 2 | Headshot | Newyork | 2026-10-05 06:55
2026-10-13 | Shift-2 | Ram Kesavan | Client Name 112 | 2000009 | 5000000009 | TBI | Flyer Project Sep 3 | Web | Mumbai | 2026-10-13 10:12
[6 empty] | TBI | Presentation template |  |  | 23-10-2026 03:29:55 AM
[6 empty] | TBI | Brochure |  |  | 23-10-2026 03:40:14 AM |  | 24-10-2026 05:00:00 PM
[6 empty] | TBI | Brochure 2 |  |  | 23-10-2026 03:43:33 AM |  | 24-10-2026 05:00:00 PM
[6 empty] | TBI | Headshot Project October |  |  | 25-10-2026 08:22:00 PM
[6 empty] | TBI | Headshot project_2 Oct |  |  | 25-10-2026 08:55:33 PM
[6 empty] | TBI | Headshot project_3 Oct |  |  | 25-10-2026 09:30:21 PM
[6 empty] | TBI | Notification Test 1002 |  |  | 25-10-2026 09:44:28 PM
[6 empty] | TBI | Notification Test 1004 |  |  | 25-10-2026 10:01:06 PM
[6 empty] | TBI | Notification Test 1005 |  |  | 25-10-2026 10:27:50 PM
[6 empty] | TBI | Notification Test 1006 |  |  | 25-10-2026 10:38:44 PM
[6 empty] | TBI | Notification Test 1007 |  |  | 25-10-2026 10:46:28 PM
[6 empty] | TBI | Notification Test 1008 |  |  | 25-10-2026 10:48:47 PM
[6 empty] | TBI | Notification Test 1009 |  |  | 25-10-2026 11:12:26 PM
[6 empty] | TBI | Notification Test 1011 |  |  | 25-10-2026 11:15:22 PM
[6 empty] | TBI | Notification Test 1012 |  |  | 25-10-2026 11:45:38 PM
[6 empty] | TBI | Notification Test 1013 |  |  | 25-10-2026 11:54:39 PM
[6 empty] | TBI | Notification Test 1014 |  |  | 26-10-2026 06:25:08 AM
[6 empty] | TBI | Notification Test 1015 |  |  | 26-10-2026 07:30:43 AM
[6 empty] | TBI | Notification Test 1016 |  |  | 26-10-2026 07:48:09 AM
[6 empty] | TBI | Notification Test 1017 |  |  | 31-10-2026 10:15:50 AM
[6 empty] | TBI | Notification Test 1018 |  |  | 31-10-2026 04:04:52 PM
[6 empty] | TBI | Notification Test 1019 |  |  | 31-10-2026 05:09:13 PM

## Completed Jobs
Date | Shift | Shift Lead | Requestor/Client Name | Project Number | WO Number | Status | Job Name | Job Type | Region | Receipt Time | Initiation Time | Deadline IST | Delivered Time | Complexity | Total Pages | Operator | QC
2026-09-01 | Shift-1 | Arjun Ramalingam | Client Name 1 | 1000000 | 6000000000 | Delivered | Brochure Project 1 | Print | Newyork | 2026-08-31 23:17 | 2026-09-01 07:21 | 2026-09-01 23:21 | 2026-09-01 21:05 | Medium | 2 | Ganesh | Arjun
2026-09-01 | Shift-1 | Arjun Ramalingam | Client Name 2 | 1000001 | 6000000001 | Delivered | Brochure Project 2 | Print | Mumbai | 2026-08-31 23:18 | 2026-09-01 07:22 | 2026-09-01 23:22 | 2026-09-01 21:06 | Simple | 4 | Kamal | Kesavan
2026-09-01 | Shift-1 | Arjun Ramalingam | Client Name 3 | 1000002 | 6000000002 | Delivered | Brochure Project 3 | Posting | London | 2026-08-31 23:19 | 2026-09-01 07:23 | 2026-09-01 23:23 | 2026-09-01 21:07 | Simple | 8 | David | Franklin
2026-09-01 | Shift-1 | Arjun Ramalingam | Client Name 4 | 1000003 | 6000000003 | Delivered | Brochure Project 4 | Web | Newyork | 2026-08-31 23:20 | 2026-09-01 07:24 | 2026-09-01 23:24 | 2026-09-01 21:08 | Complex | 4 | Govind | Mohamed
2026-09-01 | Shift-2 | Ram Kesavan | Client Name 5 | 1000004 | 6000000004 | Delivered | Brochure Project 5 | Posting | Newyork | 2026-08-31 23:21 | 2026-09-01 07:25 | 2026-09-01 23:25 | 2026-09-01 21:09 | Medium | 10 | Umasankar | Kamal
2026-09-01 | Shift-2 | Ram Kesavan | Client Name 6 | 1000005 | 6000000005 | Delivered | Brochure Project 6 | Print | Newyork | 2026-08-31 23:22 | 2026-09-01 07:26 | 2026-09-01 23:26 | 2026-09-01 21:10 | Medium | 9 | Selvam | Rajasekar
2026-09-01 | Shift-2 | Ram Kesavan | Client Name 7 | 1000006 | 6000000006 | Delivered | Brochure Project 7 | Print | Mumbai | 2026-08-31 23:23 | 2026-09-01 07:27 | 2026-09-01 23:27 | 2026-09-01 21:11 | Medium | 3 | Kamal | Ganesh
2026-09-01 | Shift-2 | Ram Kesavan | Client Name 8 | 1000007 | 6000000007 | Delivered | Brochure Project 8 | Web | London | 2026-08-31 23:24 | 2026-09-01 07:28 | 2026-09-01 23:28 | 2026-09-01 21:12 | Simple | 7 | Govind | Umasankar
2026-09-01 | Shift-3 | Amalraj Durai | Client Name 9 | 1000008 | 6000000008 | Delivered | Brochure Project 9 | Posting | Newyork | 2026-08-31 23:25 | 2026-09-01 07:29 | 2026-09-01 23:29 | 2026-09-01 21:13 | Simple | 4 | Jaiganesh | Mohamed
2026-09-01 | Shift-3 | Amalraj Durai | Client Name 10 | 1000009 | 6000000009 | Delivered | Brochure Project 10 | Print | Newyork | 2026-08-31 23:26 | 2026-09-01 07:30 | 2026-09-01 23:30 | 2026-09-01 21:14 | Complex | 4 | Sankar | Rajasekar
2026-09-01 | Shift-3 | Amalraj Durai | Client Name 11 | 1000010 | 6000000010 | Delivered | Brochure Project 11 | Print | London | 2026-08-31 23:27 | 2026-09-01 07:31 | 2026-09-01 23:31 | 2026-09-01 21:15 | Complex | 8 | Mohamed | Selvam
2026-09-01 | Shift-3 | Amalraj Durai | Client Name 12 | 1000011 | 6000000011 | Delivered | Brochure Project 12 | Web | Newyork | 2026-08-31 23:28 | 2026-09-01 07:32 | 2026-09-01 23:32 | 2026-09-01 21:16 | Simple | 6 | Franklin | Govind
2026-09-01 | Shift-3 | Amalraj Durai | Client Name 13 | 1000012 | 6000000012 | Delivered | Brochure Project 13 | Posting | Newyork | 2026-08-31 23:29 | 2026-09-01 07:33 | 2026-09-01 23:33 | 2026-09-01 21:17 | Simple | 4 | Rajasekar | Umasankar
2026-09-02 | Shift-1 | Arjun Ramalingam | Client Name 14 | 1000013 | 6000000013 | Delivered | Brochure Project 14 | Prnt | Newyork | 2026-09-01 23:17 | 2026-09-02 07:21 | 2026-09-02 23:21 | 2026-09-02 19:05 | Medium | 2 | Ganesh | Arjun
2026-09-02 | Shift-1 | Arjun Ramalingam | Client Name 15 | 1000014 | 6000000014 | Delivered | Brochure Project 15 | Print | Mumbai | 2026-09-01 23:18 | 2026-09-02 07:22 | 2026-09-02 23:22 | 2026-09-02 19:06 | Simple | 4 | Kamal | Kesavan
2026-09-02 | Shift-1 | Arjun Ramalingam | Client Name 16 | 1000015 | 6000000015 | Delivered | Brochure Project 16 | Posting | London | 2026-09-01 23:19 | 2026-09-02 07:23 | 2026-09-02 23:23 | 2026-09-02 19:07 | Simple | 8 | David | Franklin
2026-09-02 | Shift-2 | Ram Kesavan | Client Name 17 | 1000016 | 6000000016 | Delivered | Brochure Project 17 | Web | Newyork | 2026-09-01 23:20 | 2026-09-02 07:24 | 2026-09-02 23:24 | 2026-09-02 19:08 | Complex | 4 | Govind | Mohamed
2026-09-02 | Shift-2 | Ram Kesavan | Client Name 18 | 1000017 | 6000000017 | Delivered | Brochure Project 18 | Posting | Newyork | 2026-09-01 23:21 | 2026-09-02 07:25 | 2026-09-02 23:25 | 2026-09-02 19:09 | Medium | 10 | Umasankar | Kamal
2026-09-02 | Shift-2 | Ram Kesavan | Client Name 19 | 1000018 | 6000000018 | Delivered | Brochure Project 19 | Print | Newyork | 2026-09-01 23:22 | 2026-09-02 07:26 | 2026-09-02 23:26 | 2026-09-02 19:10 | Medium | 9 | Selvam | Rajasekar
2026-09-02 | Shift-2 | Ram Kesavan | Client Name 20 | 1000019 | 6000000019 | Delivered | Brochure Project 20 | Print | Mumbai | 2026-09-01 23:23 | 2026-09-02 07:27 | 2026-09-02 23:27 | 2026-09-02 19:11 | Medium | 3 | Kamal | Ganesh
2026-09-02 | Shift-2 | Ram Kesavan | Client Name 21 | 1000020 | 6000000020 | Delivered | Brochure Project 21 | Web | London | 2026-09-01 23:24 | 2026-09-02 07:28 | 2026-09-02 23:28 | 2026-09-02 19:12 | Simple | 7 | Govind | Umasankar
2026-09-02 | Shift-2 | Ram Kesavan | Client Name 22 | 1000021 | 6000000021 | Delivered | Brochure Project 22 | Posting | Newyork | 2026-09-01 23:25 | 2026-09-02 07:29 | 2026-09-02 23:29 | 2026-09-02 19:13 | Simple | 4 | Jaiganesh | Mohamed
2026-09-02 | Shift-3 | Amalraj Durai | Client Name 23 | 1000022 | 6000000022 | Delivered | Brochure Project 23 | Print | Newyork | 2026-09-01 23:26 | 2026-09-02 07:30 | 2026-09-02 23:30 | 2026-09-02 19:14 | Complex | 4 | Sankar | Rajasekar
2026-09-03 | Shift-1 | Arjun Ramalingam | Client Name 24 | 1000023 | 6000000023 | Delivered | Brochure Project 24 | Posting | Newyork | 2026-09-02 23:21 | 2026-09-03 07:25 | 2026-09-03 23:25 | 2026-09-03 22:09 | Medium | 10 | Umasankar | Kamal
2026-09-03 | Shift-2 | Ram Kesavan | Client Name 25 | 1000024 | 6000000024 | Delivered | Banner Project 1 | Print | Newyork | 2026-09-02 23:22 | 2026-09-03 07:26 | 2026-09-03 23:26 | 2026-09-03 22:10 | Medium | 9 | Selvam | Rajasekar
2026-09-03 | Shift-2 | Ram Kesavan | Client Name 26 | 1000025 | 6000000025 | Delivered | Banner Project 2 | Print | Mumbai | 2026-09-02 23:23 | 2026-09-03 07:27 | 2026-09-03 23:27 | 2026-09-03 22:11 | Medium | 3 | Kamal | Ganesh
2026-09-03 | Shift-2 | Ram Kesavan | Client Name 27 | 1000026 | 6000000026 | Delivered | Banner Project 3 | Web | London | 2026-09-02 23:24 | 2026-09-03 07:28 | 2026-09-03 23:28 | 2026-09-03 22:12 | Simple | 7 | Govind | Umasankar
2026-09-03 | Shift-2 | Ram Kesavan | Client Name 28 | 1000027 | 6000000027 | Delivered | Banner Project 4 | Posting | Newyork | 2026-09-02 23:25 | 2026-09-03 07:29 | 2026-09-03 23:29 | 2026-09-03 22:13 | Simple | 4 | Jaiganesh | Mohamed
2026-09-03 | Shift-3 | Amalraj Durai | Client Name 29 | 1000028 | 6000000028 | Delivered | Banner Project 5 | Print | Newyork | 2026-09-02 23:26 | 2026-09-03 07:30 | 2026-09-03 23:30 | 2026-09-03 22:14 | Complex | 4 | Sankar | Rajasekar
2026-09-04 | Shift-1 | Arjun Ramalingam | Client Name 30 | 1000029 | 6000000029 | Delivered | Banner Project 6 | Prnt | Newyork | 2026-09-03 23:17 | 2026-09-04 07:21 | 2026-09-04 23:21 | 2026-09-04 21:05 | Medium | 2 | Ganesh | Arjun
2026-09-04 | Shift-1 | Arjun Ramalingam | Client Name 31 | 1000030 | 6000000030 | Delivered | Banner Project 7 | Print | Mumbai | 2026-09-03 23:18 | 2026-09-04 07:22 | 2026-09-04 23:22 | 2026-09-04 21:06 | Simple | 4 | Kamal | Kesavan
2026-09-04 | Shift-1 | Arjun Ramalingam | Client Name 32 | 1000031 | 6000000031 | Delivered | Banner Project 8 | Posting | London | 2026-09-03 23:19 | 2026-09-04 07:23 | 2026-09-04 23:23 | 2026-09-04 21:07 | Simple | 8 | David | Franklin
2026-09-04 | Shift-1 | Arjun Ramalingam | Client Name 33 | 1000032 | 6000000032 | Delivered | Banner Project 9 | Web | Newyork | 2026-09-03 23:20 | 2026-09-04 07:24 | 2026-09-04 23:24 | 2026-09-04 21:08 | Complex | 4 | Govind | Mohamed
2026-09-04 | Shift-2 | Ram Kesavan | Client Name 34 | 1000033 | 6000000033 | Delivered | Banner Project 10 | Posting | Newyork | 2026-09-03 23:21 | 2026-09-04 07:25 | 2026-09-04 23:25 | 2026-09-04 21:09 | Medium | 10 | Umasankar | Kamal
2026-09-04 | Shift-2 | Ram Kesavan | Client Name 35 | 1000034 | 6000000034 | Delivered | Banner Project 11 | Print | Newyork | 2026-09-03 23:22 | 2026-09-04 07:26 | 2026-09-04 23:26 | 2026-09-04 21:10 | Medium | 9 | Selvam | Rajasekar
2026-09-04 | Shift-2 | Ram Kesavan | Client Name 36 | 1000035 | 6000000035 | Delivered | Banner Project 12 | Print | Mumbai | 2026-09-03 23:23 | 2026-09-04 07:27 | 2026-09-04 23:27 | 2026-09-04 21:11 | Medium | 3 | Kamal | Ganesh
2026-09-04 | Shift-2 | Ram Kesavan | Client Name 37 | 1000036 | 6000000036 | Delivered | Banner Project 13 | Web | London | 2026-09-03 23:24 | 2026-09-04 07:28 | 2026-09-04 23:28 | 2026-09-04 21:12 | Simple | 7 | Govind | Umasankar
2026-09-04 | Shift-3 | Amalraj Durai | Client Name 38 | 1000037 | 6000000037 | Delivered | Banner Project 14 | Posting | Newyork | 2026-09-03 23:25 | 2026-09-04 07:29 | 2026-09-04 23:29 | 2026-09-04 21:13 | Simple | 4 | Jaiganesh | Mohamed
2026-09-04 | Shift-3 | Amalraj Durai | Client Name 39 | 1000038 | 6000000038 | Delivered | Banner Project 15 | Print | Newyork | 2026-09-03 23:26 | 2026-09-04 07:30 | 2026-09-04 23:30 | 2026-09-04 21:14 | Complex | 4 | Sankar | Rajasekar
2026-09-04 | Shift-3 | Amalraj Durai | Client Name 40 | 1000039 | 6000000039 | Delivered | Banner Project 16 | Print | London | 2026-09-03 23:27 | 2026-09-04 07:31 | 2026-09-04 23:31 | 2026-09-04 21:15 | Complex | 8 | Mohamed | Selvam
2026-09-04 | Shift-3 | Amalraj Durai | Client Name 41 | 1000040 | 6000000040 | Delivered | Banner Project 17 | Web | Newyork | 2026-09-03 23:28 | 2026-09-04 07:32 | 2026-09-04 23:32 | 2026-09-04 21:16 | Simple | 6 | Franklin | Govind
2026-09-05 | Shift-1 | Arjun Ramalingam | Client Name 42 | 1000041 | 6000000041 | Delivered | Banner Project 18 | Prnt | Newyork | 2026-08-04 23:17 | 2026-09-05 07:21 | 2026-09-05 23:21 | 2026-09-05 20:05 | Medium | 2 | Ganesh | Arjun
2026-09-05 | Shift-1 | Arjun Ramalingam | Client Name 43 | 1000042 | 6000000042 | Delivered | Banner Project 19 | Print | Mumbai | 2026-08-04 23:18 | 2026-09-05 07:22 | 2026-09-05 23:22 | 2026-09-05 20:06 | Simple | 4 | Kamal | Kesavan
2026-09-05 | Shift-1 | Arjun Ramalingam | Client Name 44 | 1000043 | 6000000043 | Delivered | Banner Project 20 | Posting | London | 2026-08-04 23:19 | 2026-09-05 07:23 | 2026-09-05 23:23 | 2026-09-05 20:07 | Simple | 8 | David | Franklin
2026-09-05 | Shift-1 | Arjun Ramalingam | Client Name 45 | 1000044 | 6000000044 | Delivered | Banner Project 21 | Web | Newyork | 2026-08-04 23:20 | 2026-09-05 07:24 | 2026-09-05 23:24 | 2026-09-05 20:08 | Complex | 4 | Govind | Mohamed
2026-09-05 | Shift-2 | Ram Kesavan | Client Name 46 | 1000045 | 6000000045 | Delivered | Banner Project 22 | Posting | Newyork | 2026-08-04 23:21 | 2026-09-05 07:25 | 2026-09-05 23:25 | 2026-09-05 20:09 | Medium | 10 | Umasankar | Kamal
2026-09-05 | Shift-2 | Ram Kesavan | Client Name 47 | 1000046 | 6000000046 | Delivered | Banner Project 23 | Print | Newyork | 2026-08-04 23:22 | 2026-09-05 07:26 | 2026-09-05 23:26 | 2026-09-05 20:10 | Medium | 9 | Selvam | Rajasekar
2026-09-05 | Shift-2 | Ram Kesavan | Client Name 48 | 1000047 | 6000000047 | Delivered | Banner Project 24 | Print | Mumbai | 2026-08-04 23:23 | 2026-09-05 07:27 | 2026-09-05 23:27 | 2026-09-05 20:11 | Medium | 3 | Kamal | Ganesh
2026-09-05 | Shift-2 | Ram Kesavan | Client Name 49 | 1000048 | 6000000048 | Delivered | Banner Project 25 | Web | London | 2026-08-04 23:24 | 2026-09-05 07:28 | 2026-09-05 23:28 | 2026-09-05 20:12 | Simple | 7 | Govind | Umasankar
2026-09-05 | Shift-3 | Amalraj Durai | Client Name 50 | 1000049 | 6000000049 | Delivered | Banner Project 26 | Posting | Newyork | 2026-08-04 23:25 | 2026-09-05 07:29 | 2026-09-05 23:29 | 2026-09-05 20:13 | Simple | 4 | Jaiganesh | Mohamed
2026-09-05 | Shift-3 | Amalraj Durai | Client Name 51 | 1000050 | 6000000050 | Delivered | Banner Project 27 | Print | Newyork | 2026-08-04 23:26 | 2026-09-05 07:30 | 2026-09-05 23:30 | 2026-09-05 20:14 | Complex | 4 | Sankar | Rajasekar
2026-09-05 | Shift-3 | Amalraj Durai | Client Name 52 | 1000051 | 6000000051 | Delivered | Banner Project 28 | Print | London | 2026-08-04 23:27 | 2026-09-05 07:31 | 2026-09-05 23:31 | 2026-09-05 20:15 | Complex | 8 | Mohamed | Selvam
2026-09-05 | Shift-3 | Amalraj Durai | Client Name 53 | 1000052 | 6000000052 | Delivered | Banner Project 29 | Web | Newyork | 2026-08-04 23:28 | 2026-09-05 07:32 | 2026-09-05 23:32 | 2026-09-05 20:16 | Simple | 6 | Franklin | Govind
2026-09-05 | Shift-3 | Amalraj Durai | Client Name 54 | 1000053 | 6000000053 | Delivered | Banner Project 30 | Posting | Newyork | 2026-08-04 23:29 | 2026-09-05 07:33 | 2026-09-05 23:33 | 2026-09-05 20:17 | Simple | 4 | Rajasekar | Umasankar
2026-09-06 | Shift-1 | Arjun Ramalingam | Client Name 55 | 1000054 | 6000000054 | Delivered | Banner Project 31 | Prnt | Newyork | 2026-08-05 23:17 | 2026-09-06 07:21 | 2026-09-06 23:21 | 2026-09-06 22:05 | Medium | 2 | Ganesh | Arjun
2026-09-06 | Shift-2 | Ram Kesavan | Client Name 56 | 1000055 | 6000000055 | Delivered | Banner Project 32 | Print | Mumbai | 2026-08-05 23:18 | 2026-09-06 07:22 | 2026-09-06 23:22 | 2026-09-06 22:06 | Simple | 4 | Kamal | Kesavan
2026-09-06 | Shift-2 | Ram Kesavan | Client Name 57 | 1000056 | 6000000056 | Delivered | Banner Project 33 | Posting | London | 2026-08-05 23:19 | 2026-09-06 07:23 | 2026-09-06 23:23 | 2026-09-06 22:07 | Simple | 8 | David | Franklin
2026-09-06 | Shift-2 | Ram Kesavan | Client Name 58 | 1000057 | 6000000057 | Delivered | Banner Project 34 | Web | Newyork | 2026-08-05 23:20 | 2026-09-06 07:24 | 2026-09-06 23:24 | 2026-09-06 22:08 | Complex | 4 | Govind | Mohamed
2026-09-06 | Shift-2 | Ram Kesavan | Client Name 59 | 1000058 | 6000000058 | Delivered | Banner Project 35 | Posting | Newyork | 2026-08-05 23:21 | 2026-09-06 07:25 | 2026-09-06 23:25 | 2026-09-06 22:09 | Medium | 10 | Umasankar | Kamal
2026-09-06 | Shift-3 | Amalraj Durai | Client Name 60 | 1000059 | 6000000059 | Delivered | Banner Project 36 | Print | Newyork | 2026-08-05 23:22 | 2026-09-06 07:26 | 2026-09-06 23:26 | 2026-09-06 22:10 | Medium | 9 | Selvam | Rajasekar
2026-09-06 | Shift-3 | Amalraj Durai | Client Name 61 | 1000060 | 6000000060 | Delivered | Banner Project 37 | Print | Mumbai | 2026-08-05 23:23 | 2026-09-06 07:27 | 2026-09-06 23:27 | 2026-09-06 22:11 | Medium | 3 | Kamal | Ganesh
2026-09-06 | Shift-3 | Amalraj Durai | Client Name 62 | 1000061 | 6000000061 | Delivered | Banner Project 38 | Web | London | 2026-08-05 23:24 | 2026-09-06 07:28 | 2026-09-06 23:28 | 2026-09-06 22:12 | Simple | 7 | Govind | Umasankar
2026-09-06 | Shift-3 | Amalraj Durai | Client Name 63 | 1000062 | 6000000062 | Delivered | Banner Project 39 | Posting | Newyork | 2026-08-05 23:25 | 2026-09-06 07:29 | 2026-09-06 23:29 | 2026-09-06 22:13 | Simple | 4 | Jaiganesh | Mohamed
2026-09-07 | Shift-1 | Arjun Ramalingam | Client Name 64 | 1000063 | 6000000063 | Delivered | Banner Project 40 | Prnt | Newyork | 2026-09-06 23:17 | 2026-09-07 07:21 | 2026-09-07 23:21 | 2026-09-07 23:05 | Medium | 2 | Ganesh | Arjun
2026-09-07 | Shift-1 | Arjun Ramalingam | Client Name 65 | 1000064 | 6000000064 | Delivered | Banner Project 41 | Print | Mumbai | 2026-09-06 23:18 | 2026-09-07 07:22 | 2026-09-07 23:22 | 2026-09-07 23:06 | Simple | 4 | Kamal | Kesavan
2026-09-07 | Shift-1 | Arjun Ramalingam | Client Name 66 | 1000065 | 6000000065 | Delivered | Banner Project 42 | Posting | London | 2026-09-06 23:19 | 2026-09-07 07:23 | 2026-09-07 23:23 | 2026-09-07 23:07 | Simple | 8 | David | Franklin
2026-09-07 | Shift-1 | Arjun Ramalingam | Client Name 67 | 1000066 | 6000000066 | Delivered | Banner Project 43 | Web | Newyork | 2026-09-06 23:20 | 2026-09-07 07:24 | 2026-09-07 23:24 | 2026-09-07 23:08 | Complex | 4 | Govind | Mohamed
2026-09-07 | Shift-2 | Ram Kesavan | Client Name 68 | 1000067 | 6000000067 | Delivered | Banner Project 44 | Posting | Newyork | 2026-09-06 23:21 | 2026-09-07 07:25 | 2026-09-07 23:25 | 2026-09-07 23:09 | Medium | 10 | Umasankar | Kamal
2026-09-07 | Shift-2 | Ram Kesavan | Client Name 69 | 1000068 | 6000000068 | Delivered | Banner Project 45 | Print | Newyork | 2026-09-06 23:22 | 2026-09-07 07:26 | 2026-09-07 23:26 | 2026-09-07 23:10 | Medium | 9 | Selvam | Rajasekar
2026-09-07 | Shift-2 | Ram Kesavan | Client Name 70 | 1000069 | 6000000069 | Delivered | Banner Project 46 | Print | Mumbai | 2026-09-06 23:23 | 2026-09-07 07:27 | 2026-09-07 23:27 | 2026-09-07 23:11 | Medium | 3 | Kamal | Ganesh
2026-09-07 | Shift-2 | Ram Kesavan | Client Name 71 | 1000070 | 6000000070 | Delivered | Banner Project 47 | Web | London | 2026-09-06 23:24 | 2026-09-07 07:28 | 2026-09-07 23:28 | 2026-09-07 23:12 | Simple | 7 | Govind | Umasankar
2026-09-07 | Shift-3 | Amalraj Durai | Client Name 72 | 1000071 | 6000000071 | Delivered | Banner Project 48 | Posting | Newyork | 2026-09-06 23:25 | 2026-09-07 07:29 | 2026-09-07 23:29 | 2026-09-07 23:13 | Simple | 4 | Jaiganesh | Mohamed
2026-09-07 | Shift-3 | Amalraj Durai | Client Name 73 | 1000072 | 6000000072 | Delivered | Banner Project 49 | Print | Newyork | 2026-09-06 23:26 | 2026-09-07 07:30 | 2026-09-07 23:30 | 2026-09-07 23:14 | Complex | 4 | Sankar | Rajasekar
2026-09-07 | Shift-3 | Amalraj Durai | Client Name 74 | 1000073 | 6000000073 | Delivered | Banner Project 50 | Print | London | 2026-09-06 23:27 | 2026-09-07 07:31 | 2026-09-07 23:31 | 2026-09-07 23:15 | Complex | 8 | Mohamed | Selvam
2026-09-07 | Shift-3 | Amalraj Durai | Client Name 75 | 1000074 | 6000000074 | Delivered | Flyer Project 1 | Web | Newyork | 2026-09-06 23:28 | 2026-09-07 07:32 | 2026-09-07 23:32 | 2026-09-07 23:16 | Simple | 6 | Franklin | Govind
2026-09-08 | Shift-1 | Arjun Ramalingam | Client Name 76 | 1000075 | 6000000075 | Delivered | Flyer Project 2 | Print | Mumbai | 2026-09-07 22:23 | 2026-09-08 07:27 | 2026-09-08 22:27 | 2026-09-08 22:11 | Medium | 3 | Kamal | Ganesh
2026-09-08 | Shift-2 | Ram Kesavan | Client Name 77 | 1000076 | 6000000076 | Delivered | Flyer Project 3 | Web | London | 2026-09-07 22:24 | 2026-09-08 07:28 | 2026-09-08 22:28 | 2026-09-08 22:12 | Simple | 7 | Govind | Umasankar
2026-09-08 | Shift-2 | Ram Kesavan | Client Name 78 | 1000077 | 6000000077 | Delivered | Flyer Project 4 | Posting | Newyork | 2026-09-07 22:25 | 2026-09-08 07:29 | 2026-09-08 22:29 | 2026-09-08 22:13 | Simple | 4 | Jaiganesh | Mohamed
2026-09-08 | Shift-2 | Ram Kesavan | Client Name 79 | 1000078 | 6000000078 | Delivered | Flyer Project 5 | Print | Newyork | 2026-09-07 22:26 | 2026-09-08 07:30 | 2026-09-08 22:30 | 2026-09-08 22:14 | Complex | 4 | Sankar | Rajasekar
2026-09-08 | Shift-2 | Ram Kesavan | Client Name 80 | 1000079 | 6000000079 | Delivered | Flyer Project 6 | Print | London | 2026-09-07 22:27 | 2026-09-08 07:31 | 2026-09-08 22:31 | 2026-09-08 22:15 | Complex | 8 | Mohamed | Selvam
2026-09-08 | Shift-3 | Amalraj Durai | Client Name 81 | 1000080 | 6000000080 | Delivered | Flyer Project 7 | Web | Newyork | 2026-09-07 22:28 | 2026-09-08 07:32 | 2026-09-08 22:32 | 2026-09-08 22:16 | Simple | 6 | Franklin | Govind
2026-09-09 | Shift-1 | Arjun Ramalingam | Client Name 82 | 1000081 | 6000000081 | Delivered | Flyer Project 8 | Print | Newyork | 2026-08-08 23:17 | 2026-09-09 07:21 | 2026-09-09 23:21 | 2026-09-09 19:05 | Medium | 2 | Ganesh | Arjun
2026-09-09 | Shift-1 | Arjun Ramalingam | Client Name 83 | 1000082 | 6000000082 | Delivered | Flyer Project 9 | Print | Mumbai | 2026-08-08 23:18 | 2026-09-09 07:22 | 2026-09-09 23:22 | 2026-09-09 19:06 | Simple | 4 | Kamal | Kesavan
2026-09-09 | Shift-1 | Arjun Ramalingam | Client Name 84 | 1000083 | 6000000083 | Delivered | Flyer Project 10 | Posting | London | 2026-08-08 23:19 | 2026-09-09 07:23 | 2026-09-09 23:23 | 2026-09-09 19:07 | Simple | 8 | David | Franklin
2026-09-09 | Shift-1 | Arjun Ramalingam | Client Name 85 | 1000084 | 6000000084 | Delivered | Flyer Project 11 | Web | Newyork | 2026-08-08 23:20 | 2026-09-09 07:24 | 2026-09-09 23:24 | 2026-09-09 19:08 | Complex | 4 | Govind | Mohamed
2026-09-09 | Shift-2 | Ram Kesavan | Client Name 86 | 1000085 | 6000000085 | Delivered | Flyer Project 12 | Posting | Newyork | 2026-08-08 23:21 | 2026-09-09 07:25 | 2026-09-09 23:25 | 2026-09-09 19:09 | Medium | 10 | Umasankar | Kamal
2026-09-09 | Shift-2 | Ram Kesavan | Client Name 87 | 1000086 | 6000000086 | Delivered | Flyer Project 13 | Print | Newyork | 2026-08-08 23:22 | 2026-09-09 07:26 | 2026-09-09 23:26 | 2026-09-09 19:10 | Medium | 9 | Selvam | Rajasekar
2026-09-09 | Shift-2 | Ram Kesavan | Client Name 88 | 1000087 | 6000000087 | Delivered | Flyer Project 14 | Print | Mumbai | 2026-08-08 23:23 | 2026-09-09 07:27 | 2026-09-09 23:27 | 2026-09-09 19:11 | Medium | 3 | Kamal | Ganesh
2026-09-09 | Shift-2 | Ram Kesavan | Client Name 89 | 1000088 | 6000000088 | Delivered | Flyer Project 15 | Web | London | 2026-08-08 23:24 | 2026-09-09 07:28 | 2026-09-09 23:28 | 2026-09-09 19:12 | Simple | 7 | Govind | Umasankar
2026-09-09 | Shift-3 | Amalraj Durai | Client Name 90 | 1000089 | 6000000089 | Delivered | Flyer Project 16 | Posting | Newyork | 2026-08-08 23:25 | 2026-09-09 07:29 | 2026-09-09 23:29 | 2026-09-09 19:13 | Simple | 4 | Jaiganesh | Mohamed
2026-09-09 | Shift-3 | Amalraj Durai | Client Name 91 | 1000090 | 6000000090 | Delivered | Flyer Project 17 | Print | Newyork | 2026-08-08 23:26 | 2026-09-09 07:30 | 2026-09-09 23:30 | 2026-09-09 19:14 | Complex | 4 | Sankar | Rajasekar
2026-09-09 | Shift-3 | Amalraj Durai | Client Name 92 | 1000091 | 6000000091 | Delivered | Flyer Project 18 | Print | London | 2026-08-08 23:27 | 2026-09-09 07:31 | 2026-09-09 23:31 | 2026-09-09 19:15 | Complex | 8 | Mohamed | Selvam
2026-09-10 | Shift-1 | Arjun Ramalingam | Client Name 93 | 1000092 | 6000000092 | Delivered | Flyer Project 19 | Print | Newyork | 2026-08-09 23:17 | 2026-09-10 07:21 | 2026-09-10 23:21 | 2026-09-10 22:05 | Medium | 2 | Ganesh | Arjun
2026-09-10 | Shift-1 | Arjun Ramalingam | Client Name 94 | 1000093 | 6000000093 | Delivered | Flyer Project 20 | Print | Mumbai | 2026-08-09 23:18 | 2026-09-10 07:22 | 2026-09-10 23:22 | 2026-09-10 22:06 | Simple | 4 | Kamal | Kesavan
2026-09-10 | Shift-1 | Arjun Ramalingam | Client Name 95 | 1000094 | 6000000094 | Delivered | Flyer Project 21 | Posting | London | 2026-08-09 23:19 | 2026-09-10 07:23 | 2026-09-10 23:23 | 2026-09-10 22:07 | Simple | 8 | David | Franklin
2026-09-10 | Shift-1 | Arjun Ramalingam | Client Name 96 | 1000095 | 6000000095 | Delivered | Flyer Project 22 | Web | Newyork | 2026-08-09 23:20 | 2026-09-10 07:24 | 2026-09-10 23:24 | 2026-09-10 22:08 | Complex | 4 | Govind | Mohamed
2026-09-10 | Shift-2 | Ram Kesavan | Client Name 97 | 1000096 | 6000000096 | Delivered | Flyer Project 23 | Posting | Newyork | 2026-08-09 23:21 | 2026-09-10 07:25 | 2026-09-10 23:25 | 2026-09-10 22:09 | Medium | 10 | Umasankar | Kamal
2026-09-10 | Shift-2 | Ram Kesavan | Client Name 98 | 1000097 | 6000000097 | Delivered | Flyer Project 24 | Print | Newyork | 2026-08-09 23:22 | 2026-09-10 07:26 | 2026-09-10 23:26 | 2026-09-10 22:10 | Medium | 9 | Selvam | Rajasekar
2026-09-10 | Shift-2 | Ram Kesavan | Client Name 99 | 1000098 | 6000000098 | Delivered | Flyer Project 25 | Print | Mumbai | 2026-08-09 23:23 | 2026-09-10 07:27 | 2026-09-10 23:27 | 2026-09-10 22:11 | Medium | 3 | Kamal | Ganesh
2026-09-10 | Shift-2 | Ram Kesavan | Client Name 100 | 1000099 | 6000000099 | Delivered | Flyer Project 26 | Web | London | 2026-08-09 23:24 | 2026-09-10 07:28 | 2026-09-10 23:28 | 2026-09-10 22:12 | Simple | 7 | Govind | Umasankar
2026-09-10 | Shift-3 | Amalraj Durai | Client Name 101 | 1000100 | 6000000100 | Delivered | Flyer Project 27 | Posting | Newyork | 2026-08-09 23:25 | 2026-09-10 07:29 | 2026-09-10 23:29 | 2026-09-10 22:13 | Simple | 4 | Jaiganesh | Mohamed
2026-09-10 | Shift-3 | Amalraj Durai | Client Name 102 | 1000101 | 6000000101 | Delivered | Flyer Project 28 | Print | Newyork | 2026-08-09 23:26 | 2026-09-10 07:30 | 2026-09-10 23:30 | 2026-09-10 22:01 | Complex | 4 | Sankar | Rajasekar

## Dropdown
Operator | QC
Ganesh | Arjun
Kamal | Kesavan
David | Franklin
Govind | Mohamed
Umasankar | Kamal
Selvam | Rajasekar
Kamal | Ganesh
Govind | Umasankar
Jaiganesh | Mohamed
Sankar | Rajasekar
Mohamed | Selvam
Franklin | Govind
Rajasekar | Umasankar
Ganesh | Arjun